## Report
DAILY PROGRESS REPORT
Project |  | Project 01 |  |  | Date:
Client: |  |  |  |  | Contractor:
Date of Coverage:
A. WEATHER CONDITION: |  |  |  |  | Temperature(°C): |  |  | Max: | 16 | Min: | 9
B1. MANPOWER (Project Management Team):
Sr. PM | PL. M | [8 empty] | TOTAL
1 | 1 | [8 empty] | 2
B2. MANPOWER (Site Management Team):
SM | Site. Sup | QC | [7 empty] | TOTAL
1 | 11 | 4 | [7 empty] | 16
B3. MANPOWER (Installation):
Worker | Foreman | Welder | [7 empty] | TOTAL
27 | 3 | 1 | [7 empty] | 31
GRAND TOTAL: |  |  | 49
C. WORK PERFORMED - QUANTITY:
Activity ID | DESCRIPTION |  |  | LOCATION |  | Total Qty | Unit | Prev. Cum. Qty. | Today Qty | Cum. Qty | Cum. % | .
| Copping panels installation |  |  | L31 |  | 8 | Nos | 8 | 0 | 8 | 100%
| Replacement of SDR Glass |  |  | L29 |  | 29 | Nos | 10 | 0 | 10 | 34.48%
| Replacement of Tower Glass |  |  | L30 |  | 5 | Nos | 2 | 0 | 2 | 40%
| Setting out of Brackets ongoing |  |  | L3 |  | 252 | Nos | 40 | 0 | 40 | 15.87%
D. WORK PERFORMED - MANHOURS:
Activity ID | DESCRIPTION |  |  |  |  | LOCATION |  |  | Prev. Cum. Hrs. | Today Hrs. | Cum. Hrs.
| Copping panels installation |  |  |  |  | L31 |  |  | 250 | 0 | 250
| Replacement of SDR Glass |  |  |  |  | L29 |  |  | 366 | 0 | 366
| Replacement of Tower Glass |  |  |  |  | L30 |  |  | 40 | 0 | 40
Total | [8 empty] | 656 | 0 | 656
E. WORK TO BE PERFORMED ON THE FOLLOWING DAY:
Activity ID | DESCRIPTION |  |  |  |  | LOCATION |  |  |  |  | QTY
F. MAJOR EQUIPMENT (By Client / Main Contractor):
NO. | DESCRIPTION |  |  |  | NO. | DESCRIPTION |  |  |  |  | QTY
1 |  |  |  |  | 5
2 |  |  |  |  | 6
3 |  |  |  |  | 7
4 |  |  |  |  | 8
G. MATERIALS DELIVERED TO SITE:
ITEM | DESCRIPTION |  |  |  |  | MIR NO. |  |  |  |  | QTY
H. LOST HOURS (Crane, Access, etc.)
Prepared by:
|  | Name |  | Position |  |  |  | Signature |  | Date
Approved by:
|  | Name |  | Position |  |  |  | Signature |  | Date
Rainy
Windy
Sunny
Dusty

## Photos
Site Photos